## Plan Control
FIELD | VALUE
plan_id | MIG-PLAN-2026-001
template_version | 1.0.0
plan_version | 3
status | ready_for_approval
created_at_utc | 2026-07-20T09:00:00Z
updated_at_utc | 2026-08-01T12:00:00Z
migration_owner | PERSON-MIGRATION-OWNER
decision_owner | PERSON-DECISION-OWNER
purpose | Move approved fictional customer and order records between bounded systems with reviewable transformations and reconciliation.
included_datasets | DATASET-CUSTOMERS ¦ DATASET-ORDERS
excluded_work | Website content, domain, redirect, analytics, and SEO relocation ¦ Ongoing synchronization, replication, or change data capture ¦ Provider credential setup and a native migration-service claim
website_relocation_included | false
ongoing_synchronization_included | false
native_migration_service_claimed | false

## Field Mapping
mapping_id | dataset_id | source_field | target_field | transformation_kind | transformation_expression | transformation_version | owner_id | privacy_classification | purpose | retention_action | retention_until | access_owner_id
MAP-CUSTOMER-ID | DATASET-CUSTOMERS | legacy_customer_id | customer_id | direct | copy canonical string | 1 | PERSON-MIGRATION-OWNER | internal | record identity | retain | 2028-12-31 | PERSON-PRIVACY-OWNER
MAP-CUSTOMER-NAME | DATASET-CUSTOMERS | full_name | display_name | normalize | trim and collapse whitespace | 2 | PERSON-DATA-OWNER | personal | customer account display | retain | 2027-12-31 | PERSON-PRIVACY-OWNER
MAP-CUSTOMER-EMAIL | DATASET-CUSTOMERS | email | email_normalized | normalize | trim and lowercase | 3 | PERSON-DATA-OWNER | personal | account contact | review_then_delete | 2027-06-30 | PERSON-PRIVACY-OWNER
MAP-CUSTOMER-STATUS | DATASET-CUSTOMERS | status | lifecycle_status | lookup | active to active; archived to archived | 1 | PERSON-DATA-OWNER | internal | account lifecycle | retain | 2028-12-31 | PERSON-PRIVACY-OWNER
MAP-CUSTOMER-BALANCE | DATASET-CUSTOMERS | legacy_balance_cents | opening_balance_cents | direct | copy integer cents | 1 | PERSON-FINANCE-OWNER | confidential | opening balance reconciliation | retain | 2029-12-31 | PERSON-FINANCE-OWNER
MAP-ORDER-ID | DATASET-ORDERS | legacy_order_id | order_id | direct | copy canonical string | 1 | PERSON-MIGRATION-OWNER | internal | record identity | retain | 2029-12-31 | PERSON-PRIVACY-OWNER
MAP-ORDER-CUSTOMER | DATASET-ORDERS | legacy_customer_id | customer_id | reference | map through MAP-CUSTOMER-ID | 1 | PERSON-DATA-OWNER | internal | customer relationship | retain | 2029-12-31 | PERSON-PRIVACY-OWNER
MAP-ORDER-TOTAL | DATASET-ORDERS | total_cents | order_total_cents | direct | copy integer cents | 1 | PERSON-FINANCE-OWNER | confidential | order balance reconciliation | retain | 2029-12-31 | PERSON-FINANCE-OWNER
MAP-ORDER-CREATED | DATASET-ORDERS | created_local | created_at_utc | datetime | parse America/New_York then convert to UTC | 2 | PERSON-DATA-OWNER | internal | order chronology | retain | 2029-12-31 | PERSON-PRIVACY-OWNER
MAP-ORDER-STATE | DATASET-ORDERS | state | order_state | lookup | paid to settled; void to excluded | 2 | PERSON-DATA-OWNER | internal | order lifecycle | retain | 2029-12-31 | PERSON-PRIVACY-OWNER

## Count Reconciliation
DATASET_ID | NAME | SOURCE_COUNT | EXCLUDED_COUNT | EXPECTED_TARGET | ACTUAL_TARGET | DELTA | TOLERANCE | STATUS | SOURCE_CHECKSUM | TARGET_CHECKSUM
DATASET-CUSTOMERS | Customer accounts | 1250 | 20 | 1230 | 1230 | 0 | 0 | pass | sha256:1111111111111111111111111111111111111111111111111111111111111111 | sha256:2222222222222222222222222222222222222222222222222222222222222222
DATASET-ORDERS | Order records | 5000 | 125 | 4875 | 4875 | 0 | 0 | pass | sha256:3333333333333333333333333333333333333333333333333333333333333333 | sha256:4444444444444444444444444444444444444444444444444444444444444444

## Balance Checks
DATASET_ID | BALANCE_ID | METRIC | UNIT | BEFORE | EXCLUDED | ADJUSTMENT | EXPECTED_AFTER | ACTUAL_AFTER | DELTA | TOLERANCE | STATUS | OWNER_ID
DATASET-CUSTOMERS | BAL-CUSTOMER-OPENING | opening_balance_cents | integer cents | 48275000 | 100000 | 0 | 48175000 | 48175000 | 0 | 0 | pass | PERSON-FINANCE-OWNER
DATASET-ORDERS | BAL-ORDER-TOTAL | order_total_cents | integer cents | 329500000 | 1250000 | 0 | 328250000 | 328250000 | 0 | 0 | pass | PERSON-FINANCE-OWNER

## Privacy Retention
RETENTION_ID | DATASET_ID | FIELD_MAPPING_IDS | CLASSIFICATION | PURPOSE | SOURCE_RETAIN_UNTIL | TARGET_RETAIN_UNTIL | SOURCE_DISPOSITION | TARGET_DISPOSITION | ACCESS_OWNER | REVIEW_AT
RET-CUSTOMER-CONTACT | DATASET-CUSTOMERS | MAP-CUSTOMER-NAME ¦ MAP-CUSTOMER-EMAIL | personal | customer account display and contact | 2027-06-30 | 2027-06-30 | delete after approved reconciliation hold | review then delete when purpose ends | PERSON-PRIVACY-OWNER | 2026-12-15
RET-CUSTOMER-BALANCE | DATASET-CUSTOMERS | MAP-CUSTOMER-BALANCE | confidential | opening balance reconciliation | 2029-12-31 | 2029-12-31 | archive under approved financial policy | retain under approved financial policy | PERSON-FINANCE-OWNER | 2026-12-15
RET-BALANCES | DATASET-ORDERS | MAP-ORDER-TOTAL | confidential | order balance reconciliation | 2029-12-31 | 2029-12-31 | archive under approved financial policy | retain under approved financial policy | PERSON-FINANCE-OWNER | 2026-12-15

## Trial Runs
RUN_ID | STARTED_AT_UTC | COMPLETED_AT_UTC | DATASET_IDS | SOURCE_SNAPSHOT_REF | STATUS | FAILURE_IDS | EVIDENCE_REF | REVIEWER_ID
RUN-TRIAL-001 | 2026-07-25T09:00:00Z | 2026-07-25T10:15:00Z | DATASET-CUSTOMERS ¦ DATASET-ORDERS | snapshot://fictional-test/2026-07-25-a | failed | FAIL-001 | evidence://trial/001 | PERSON-MIGRATION-OWNER
RUN-TRIAL-002 | 2026-07-29T09:00:00Z | 2026-07-29T10:20:00Z | DATASET-CUSTOMERS ¦ DATASET-ORDERS | snapshot://fictional-test/2026-07-29-b | passed |  | evidence://trial/002 | PERSON-MIGRATION-OWNER

## Cutover
STEP_ID | SEQUENCE | ACTION | OWNER_ID | DEPENDS_ON | EXPECTED_EVIDENCE | STATUS
CUT-01 | 1 | Freeze approved source writes and record the final source position. | PERSON-DATA-OWNER |  | evidence://cutover/write-freeze | pending
CUT-02 | 2 | Create and verify the final bounded source snapshot. | PERSON-MIGRATION-OWNER | CUT-01 | evidence://cutover/final-snapshot | pending
CUT-03 | 3 | Run the approved export, transformations, and target import. | PERSON-MIGRATION-OWNER | CUT-02 | evidence://cutover/import-log | pending
CUT-04 | 4 | Reconcile counts, checksums, before and after balances, and relationships. | PERSON-FINANCE-OWNER | CUT-03 | evidence://cutover/reconciliation | pending
CUT-05 | 5 | Run bounded functional, access, privacy, failure, and restore checks. | PERSON-PRIVACY-OWNER | CUT-04 | evidence://cutover/readiness | pending
CUT-06 | 6 | Record the named human go, hold, or rollback decision. | PERSON-DECISION-OWNER | CUT-05 | evidence://cutover/decision | pending
CUT-07 | 7 | Change the approved application connection only after a go decision. | PERSON-MIGRATION-OWNER | CUT-06 | evidence://cutover/connection | pending
CUT-08 | 8 | Observe errors, record deltas, access, and business balances before source retirement. | PERSON-DATA-OWNER | CUT-07 | evidence://cutover/observation | pending

## Rollback
STEP_ID | SEQUENCE | ACTION | OWNER_ID | DEPENDS_ON | EXPECTED_EVIDENCE
ROLL-01 | 1 | Decision owner records rollback and stops target writes. | PERSON-DECISION-OWNER |  | evidence://rollback/decision
ROLL-02 | 2 | Export post-cutover target deltas to a bounded quarantine record. | PERSON-MIGRATION-OWNER | ROLL-01 | evidence://rollback/delta-export
ROLL-03 | 3 | Restore and verify the approved source recovery point. | PERSON-MIGRATION-OWNER | ROLL-02 | evidence://rollback/source-restore
ROLL-04 | 4 | Reconnect the application to the verified source and run bounded smoke checks. | PERSON-DATA-OWNER | ROLL-03 | evidence://rollback/source-smoke
ROLL-05 | 5 | Reconcile quarantined deltas and open follow-up decisions without automatic replay. | PERSON-DECISION-OWNER | ROLL-04 | evidence://rollback/delta-review
TRIGGER_ID | METRIC | THRESHOLD | OWNER_ID
ROLL-TRIGGER-COUNT | any dataset count or balance delta | greater than zero after one bounded recheck | PERSON-FINANCE-OWNER
ROLL-TRIGGER-ACCESS | unauthorized access or missing required record relationship | one confirmed event | PERSON-PRIVACY-OWNER
RECOVERY_POINT | snapshot://fictional-test/final-approved-source
CHANGED_DATA_STRATEGY | Stop target writes, export approved post-cutover deltas to a quarantine record, restore the source recovery point, review each delta before any replay, and never dual-write without a separate design and test plan.

## Failure Log
FAILURE_ID | RUN_ID | DATASET_ID | DETECTED_AT_UTC | SEVERITY | TYPE | DESCRIPTION | EVIDENCE_REF | OWNER_ID | STATUS | RESOLVED_AT_UTC | RESOLUTION | RELATED_MAPPINGS
FAIL-001 | RUN-TRIAL-001 | DATASET-ORDERS | 2026-07-25T09:40:00Z | high | transformation_mismatch | A nonexistent local time was accepted instead of being quarantined. | evidence://failure/001 | PERSON-DATA-OWNER | resolved | 2026-07-28T16:00:00Z | Transformation version 2 rejects nonexistent local times; trial run 002 passed the retest. | MAP-ORDER-CREATED

## Exceptions
EXCEPTION_ID | DATASET_ID | RECORD_COUNT | BALANCE_IMPACT | REASON | OWNER_ID | APPROVED_BY | STATUS
EXC-CUSTOMER-TEST | DATASET-CUSTOMERS | 20 | 100000 | Fictional test accounts excluded under the approved minimum-purpose rule. | PERSON-DATA-OWNER | PERSON-DECISION-OWNER | approved
EXC-ORDER-VOID | DATASET-ORDERS | 125 | 1250000 | Fictional void orders excluded from the target opening ledger. | PERSON-FINANCE-OWNER | PERSON-DECISION-OWNER | approved