## Risks
riskId | title | category | status | ownerId | reviewOwnerId | identifiedAt | lastReviewedAt | nextReviewAt | currentRevision | inherentProbability | inherentImpact | inherentScore | inherentRating | responseType | responseOwnerId | responseAction | trigger | triggerStatus | escalation | residualProbability | residualImpact | residualScore | residualRating | acceptanceDecisionOwnerId | acceptanceReason | closedAt | closureReason
risk-dependency-migration | Dependency migration misses the integration window | delivery | monitoring | owner-delivery | owner-program | 2026-07-18T09:00:00Z | 2026-08-01T10:00:00Z | 2026-08-15T10:00:00Z | 2 | 4 | 4 | 16 | high | reduce | owner-delivery | Run the compatibility rehearsal before the vendor cutoff | Vendor sandbox removes the current API version | not_triggered | Escalate to the program owner and activate the staged fallback | 2 | 4 | 8 | medium
risk-accessibility-regression | Keyboard navigation regresses during the interface update | quality | responding | owner-quality | owner-product | 2026-07-21T11:00:00Z | 2026-08-01T10:15:00Z | 2026-08-12T10:00:00Z | 2 | 3 | 4 | 12 | high | reduce | owner-quality | Run manual keyboard checks on changed journeys | Any required journey loses visible focus or keyboard completion | not_triggered | Stop the release candidate and return the defect to its implementation owner | 2 | 3 | 6 | medium
risk-provider-outage | External notification provider is unavailable during launch | operations | monitoring | owner-operations | owner-program | 2026-07-22T14:00:00Z | 2026-08-01T10:30:00Z | 2026-08-08T10:00:00Z | 2 | 3 | 3 | 9 | medium | share | owner-operations | Keep a bounded retry queue and documented manual contact path | Provider health check fails for two consecutive intervals | watching | Escalate to the incident owner and pause nonessential sends | 2 | 2 | 4 | low
risk-training-gap | Operators need more time to learn the changed review flow | adoption | monitoring | owner-operations | owner-product | 2026-07-24T08:30:00Z | 2026-08-01T10:45:00Z | 2026-08-15T10:00:00Z | 2 | 3 | 2 | 6 | medium | accept | owner-product | Keep guided practice and office hours available | More than two fictional rehearsal tasks need moderator correction | not_triggered | Escalate the training plan for a human release-readiness decision | 3 | 2 | 6 | medium | owner-program | The named owner accepts the remaining training uncertainty only for the next planning review

## History
eventId | riskId | revision | eventType | occurredAt | actorRoleId | summary | evidenceRef
event-dependency-1 | risk-dependency-migration | 1 | identified | 2026-07-18T09:00:00Z | owner-delivery | Recorded the vendor cutoff scenario | https://evidence.example.test/risk/dependency/identified
event-dependency-2 | risk-dependency-migration | 2 | reviewed | 2026-08-01T10:00:00Z | owner-program | Confirmed the rehearsal response and residual estimate | https://evidence.example.test/risk/dependency/review-2
event-accessibility-1 | risk-accessibility-regression | 1 | identified | 2026-07-21T11:00:00Z | owner-quality | Recorded the changed keyboard journey scenario | https://evidence.example.test/risk/accessibility/identified
event-accessibility-2 | risk-accessibility-regression | 2 | response_updated | 2026-08-01T10:15:00Z | owner-quality | Added manual keyboard review and release-stop escalation | https://evidence.example.test/risk/accessibility/review-2
event-provider-1 | risk-provider-outage | 1 | identified | 2026-07-22T14:00:00Z | owner-operations | Recorded the external notification dependency | https://evidence.example.test/risk/provider/identified
event-provider-2 | risk-provider-outage | 2 | reviewed | 2026-08-01T10:30:00Z | owner-program | Confirmed retry and manual contact boundaries | https://evidence.example.test/risk/provider/review-2
event-training-1 | risk-training-gap | 1 | identified | 2026-07-24T08:30:00Z | owner-operations | Recorded the fictional operator rehearsal concern | https://evidence.example.test/risk/training/identified
event-training-2 | risk-training-gap | 2 | response_accepted | 2026-08-01T10:45:00Z | owner-program | Recorded a bounded acceptance reason and next review | https://evidence.example.test/risk/training/review-2

## Scoring
TYPE | VALUE | RANGE | USE
method | score = probability * impact | 1-25 | Transparent prioritization only; never an automatic decision
probability | 1 rare | 1 | Local example label; adapt to the planning horizon
probability | 2 unlikely | 2 | Local example label; adapt to the planning horizon
probability | 3 possible | 3 | Local example label; adapt to the planning horizon
probability | 4 likely | 4 | Local example label; adapt to the planning horizon
probability | 5 almost certain | 5 | Local example label; adapt to the planning horizon
impact | 1 negligible | 1 | Use the highest credible consequence in the named context
impact | 2 minor | 2 | Use the highest credible consequence in the named context
impact | 3 moderate | 3 | Use the highest credible consequence in the named context
impact | 4 major | 4 | Use the highest credible consequence in the named context
impact | 5 severe | 5 | Use the highest credible consequence in the named context
rating | low | 1-4 | Routine review; never a pass or approval
rating | medium | 5-9 | Named owner review
rating | high | 10-16 | Active response and specific escalation
rating | critical | 17-25 | Immediate named-owner escalation