## Overview
field | value
planId | plan-checkout-2026-08
title | Fictional checkout recovery release
version | 3
timezone | UTC
baselineDate | 2026-08-01
deliveryStart | 2026-08-03
deliveryEnd | 2026-08-28
ownerId | owner-delivery
status | approved_for_delivery
boundary | Not a PRD, capacity plan, staffing decision, authorization, or guarantee.

## Owners
id | name | role
owner-delivery | Delivery lead | plan and release owner
owner-product | Product lead | scope and acceptance owner
owner-engineering | Engineering lead | implementation owner
owner-quality | Quality lead | test evidence owner
owner-operations | Operations lead | deployment and recovery owner

## Delivery Work Items
id | parentId | sequence | workstream | title | description | ownerId | status | plannedStart | plannedEnd | milestoneId | acceptanceIds | riskIds | releaseId
work-discovery |  | 10 | definition | Freeze accepted recovery behavior | Link the approved requirement and acceptance records without rewriting them. | owner-product | done | 2026-08-03 | 2026-08-05 | milestone-scope | accept-scope | risk-scope-drift | release-checkout-v3
work-api |  | 20 | implementation | Implement retry-safe recovery endpoint | Add version checks, idempotent retries, audit events, and bounded failure responses. | owner-engineering | done | 2026-08-06 | 2026-08-12 | milestone-build | accept-api-retry¦accept-audit | risk-duplicate-side-effect | release-checkout-v3
work-ui |  | 30 | implementation | Add recovery status and operator controls | Show current state, retry boundaries, and human escalation without claiming automatic success. | owner-engineering | done | 2026-08-06 | 2026-08-13 | milestone-build | accept-ui-state | risk-stale-status | release-checkout-v3
work-test |  | 40 | verification | Run integration and recovery tests | Exercise happy, invalid, duplicate, out-of-order, partial-failure, smoke, and rollback paths. | owner-quality | done | 2026-08-14 | 2026-08-19 | milestone-verified | accept-integration¦accept-recovery | risk-test-environment | release-checkout-v3
work-release |  | 50 | release | Authorize and execute bounded release | Confirm evidence, owner decisions, monitoring, rollback trigger, and the exact release artifact. | owner-operations | ready | 2026-08-20 | 2026-08-21 | milestone-release-ready | accept-release-gates | risk-rollback-fails | release-checkout-v3

## Dependencies
id | predecessorId | successorId | type | lagDays | rationale
dependency-scope-api | work-discovery | work-api | finish_to_start | 0 | Implementation follows the accepted behavior baseline.
dependency-scope-ui | work-discovery | work-ui | finish_to_start | 0 | Visible state must follow the same accepted behavior baseline.
dependency-api-test | work-api | work-test | finish_to_start | 1 | Integration tests require the recovery endpoint.
dependency-ui-test | work-ui | work-test | finish_to_start | 0 | Recovery state tests require operator controls.
dependency-test-release | work-test | work-release | finish_to_start | 1 | Release authorization requires reviewed test evidence.

## Milestones
id | name | ownerId | targetDate | workItemIds | acceptanceIds | exitDecision
milestone-scope | Scope baseline accepted | owner-product | 2026-08-05 | work-discovery | accept-scope | Product lead confirms the accepted requirement and exclusion links.
milestone-build | Recovery path implemented | owner-engineering | 2026-08-13 | work-api¦work-ui | accept-api-retry¦accept-audit¦accept-ui-state | Engineering lead confirms implementation review and reproducible checks.
milestone-verified | Recovery evidence reviewed | owner-quality | 2026-08-19 | work-test | accept-integration¦accept-recovery | Quality lead records the environment, artifact, results, and known limits.
milestone-release-ready | Release decision ready | owner-delivery | 2026-08-21 | work-release | accept-release-gates | Delivery lead records the explicit release decision and exact rollback trigger.

## Acceptance
id | workItemId | statement | evidenceOwnerId | evidenceRef | status
accept-scope | work-discovery | Accepted behavior and exclusions link to versioned requirement records. | owner-product | https://evidence.example.test/requirements/recovery-v3 | accepted
accept-api-retry | work-api | Duplicate recovery requests reuse the original result or return a version conflict. | owner-quality | https://evidence.example.test/tests/api-retry-v3 | accepted
accept-audit | work-api | Every state change records actor, target version, outcome, and correlation ID. | owner-quality | https://evidence.example.test/tests/audit-v3 | accepted
accept-ui-state | work-ui | The operator sees pending, completed, failed, and manual-review states without false success. | owner-quality | https://evidence.example.test/tests/ui-state-v3 | accepted
accept-integration | work-test | Happy, invalid, duplicate, out-of-order, and partial-failure paths pass in the named environment. | owner-quality | https://evidence.example.test/runs/integration-v3 | accepted
accept-recovery | work-test | Rollback rehearsal restores the known fixture and the verification query reconciles it. | owner-operations | https://evidence.example.test/runs/rollback-v3 | accepted
accept-release-gates | work-release | Every required gate has current evidence, a named owner, and ready status. | owner-delivery | https://evidence.example.test/releases/checkout-v3 | accepted

## Risks
id | description | ownerId | probability | impact | response | trigger | mitigation | contingency | status | reviewDate
risk-scope-drift | A late behavior change invalidates accepted evidence. | owner-product | medium | high | mitigate | Requirement version differs from the delivery baseline. | Stop the release and rebaseline affected work and acceptance links. | Move the change to a later plan version. | open | 2026-08-18
risk-duplicate-side-effect | A retry applies the recovery action more than once. | owner-engineering | low | high | mitigate | The same request fingerprint produces multiple state transitions. | Persist one idempotency result per version and fingerprint. | Stop writes and reconcile from the audit event trail. | open | 2026-08-18
risk-stale-status | The interface shows an older recovery state. | owner-engineering | medium | medium | mitigate | Displayed version differs from the latest server event. | Render server version and refresh after every transition. | Disable operator actions and require a manual refresh. | open | 2026-08-18
risk-test-environment | The test environment does not match the release artifact. | owner-quality | low | high | avoid | Artifact digest or configuration differs from the evidence record. | Fail the run before tests and record the exact digest and environment. | Recreate the environment from the release candidate. | open | 2026-08-19
risk-rollback-fails | The bounded rollback does not restore the known fixture. | owner-operations | low | critical | mitigate | Post-rollback verification differs from the recorded fixture. | Rehearse the exact rollback plan before authorization. | Keep traffic held and escalate to the named incident owner. | open | 2026-08-20

## Release Gates
id | type | name | ownerId | evidenceRef | required | status
gate-acceptance | acceptance | Acceptance evidence reviewed | owner-product | https://evidence.example.test/releases/checkout-v3/acceptance | true | ready
gate-security | security | Security and privacy boundary reviewed | owner-engineering | https://evidence.example.test/releases/checkout-v3/security | true | ready
gate-deployment | deployment | Exact artifact and deployment plan recorded | owner-operations | https://evidence.example.test/releases/checkout-v3/deployment | true | ready
gate-rollback | rollback | Rollback rehearsal and trigger reviewed | owner-operations | https://evidence.example.test/releases/checkout-v3/rollback | true | ready